## Project BUDGET
| automatic formulas | local /contract currency | remaining funds | % of Time * NB of staff |  | RATE XAF/EURO | 655.957 | you use an ext. office to sub contract your adm. activities
FUNCTION | NAME | CONTRACT DURATION (MONTHS) | MONTHLY GROSS SALARY (EURO) | % TIME on PROJECT | MONTHLY NET SALARY (EURO) | MONTHLY NET SALARY (XAF) | BUDGET PERIODE 1 Year 1 | REAL EXPENSES 1st semester Year 1 | BUDGET PERIODE 2 Year 2 | BUDGET PERIODE 3 Year 3
2 interviewers for baseline studies | to be recruited | 24 | 600 | 100% | 600 | 393574.2 | 4722890.4 | 300000 | 4722890.4 | 0 | NB: contract signed for 24 months so no expenses in Year 3
driver for field work |  | 24 | 600 | 100% | 600 | 393574.2 | 4722890.4 | 0 | 4722890.4 | 0 | NB: contract signed for 24 months so no expenses in Year 3
1 Post Doc disease 2 |  | 24 | 280 | 100% | 280 | 183667.96 | 2204015.52 | 0 | 2204015.52 | 0 | NB: contract signed for 24 months so no expenses in Year 3
1 Junior Doctor disease 2 |  | 24 | 200 | 200% | 400 | 262382.8 | 3148593.6 | 0 | 3148593.6 | 0 | NB: contract signed for 24 months so no expenses in Year 3
1 nurse Lab disease 2 |  | 24 | 250 | 100% | 250 | 163989.25 | 1967871 | 0 | 1967871 | 0 | NB: contract signed for 24 months so no expenses in Year 3
Data Manager-Coordination |  | 24 | 600 | 100% | 600 | 393574.2 | 4722890.4 | 0 | 4722890.4 | 0 | NB: contract signed for 24 months so no expenses in Year 3
Local Coordinator disease 1 |  | 24 | 600 | 100% | 600 | 393574.2 | 4722890.4 | 0 | 4722890.4 | 0 | NB: contract signed for 24 months so no expenses in Year 3
Clinical researcher |  | 24 | 280 | 100% | 280 | 183667.96 | 2204015.52 | 0 | 2204015.52 | 0 | NB: contract signed for 24 months so no expenses in Year 3
1 technician Lab disease 1 |  | 24 | 200 | 100% | 200 | 131191.4 | 524765.6 | 0 | 1311914 | 1311914 | Expected to start in sept year 1
4 PhD students |  | 36 | 1500 | 20% | 300 | 196787.1 | 2361445.2 | 1560000 | 2361445.2 | 2361445.2
Bioststistician |  | 36 | 1000 | 100% | 1000 | 655957 | 7871484 | 3250000 | 7871484 | 7871484
finance officer |  | 36 | 280 | 100% | 280 | 183667.96 | 2204015.52 | 0 | 2204015.52 | 2204015.52
Project Manager |  | 36 | 1600 | 100% | 1600 | 1049531.2 | 12594374.4 | 1560000 | 12594374.4 | 12594374.4
1 lab technicien disease 2 |  | 36 | 380 | 50% | 190 | 124631.83 | 1495581.96 | 0 | 1495581.96 | 1495581.96
Local Coordinator disease 2 |  | 36 | 2500 | 20% | 500 | 327978.5 | 3935742 | 437500 | 3935742 | 3935742
TOTAL PERSONEL COST (XAF) | [5 empty] | 5037749.76 | 59403465.92 | 7107500 | 60190614.32 | 31774557.08
TOTAL PERSONEL COST (EURO) |  |  |  |  | 7680 | 7680 | 90560 | 10835.3139 | 91760 | 48440
*SUB CONTRACT offices (XAF) | [6 empty] | 26103638 | 10758690 | 16398925 | 12069608.8 | * See details in monthly budget sub contract
SUB CONTRACT offices (EURO) | [6 empty] | 39794.7396 | 16401.5172 | 25000 | 18400
OVERHEADS for administration (XAF) | [6 empty] | 12793300 | 12713710
OVERHEADS for administration (EURO) | [6 empty] | 19503.2601 | 19381.9259
Car purchase for HIV/AIDS & TB studies |  | 12
CAR PURCHASE (XAF) | [6 empty] | 16398925 | 0 | 0 | 0
CAR PURCHASE (EURO) | [6 empty] | 25000 | 0 | 0 | 0
Laboratory personnel | Molecular Diagnostics of disease 1 | 12 |  |  |  |  | 13578309.9 | 0 | 0 | 0
nurses , MDs, researchers | Preparation of SOP for disease 1 | 12 |  |  |  |  | 14234266.9 | 0 | 0 | 0
Laboratory personnel | In vitro culture of Myc.Bac. And drug sensitivity | 12 |  |  |  |  | 0 | 0 | 13578309.9 | 0
Laboratory personnel | Spoligotyping and drug resistance genotyping | 12 |  |  |  |  | 0 | 0 | 13512714.2 | 0
TOTAL short term Training (XAF) | [6 empty] | 27812576.8 | 0 | 27091024.1 | 0
TOTAL short term Training (EURO) | [6 empty] | 42400 | 0 | 41300 | 0
renovation WC + office |  | 36 | [5 empty] | 1949250
Internet ( installation+monthly due)+ sattelite dish |  | 36 | [5 empty] | 4446950
purchase / installation generator group |  | 36 | [5 empty] | 834000
renovation Hospital Laboratory |  | 36 | [5 empty] | 0
renovation Lab P2 University |  | 36 | [5 empty] | 0
TOTAL RENOVATION (XAF) | [6 empty] | 39357420 | 7230200 | 39357420 | 0
TOTAL RENOVATION (EURO) | [6 empty] | 60000 | 11022.3688 | 60000 | 0
Feezers, fridges, power supply, hoods, microscopes, PCR machines, electrophoresis equipment, HPLC machine, haematological analyser FACS machine |  | 36 | [5 empty] | 0
TOTAL COST LAB EQUIPMENTS (XAF) | [6 empty] | 9839355 | 0 | 6559570 | 3279785
TOTAL COST LAB EQUIPMENTS (EURO) | [6 empty] | 15000 | 0 | 10000 | 5000
study 1: Preparation for phase III disease 1 vaccine/drug trial site: to determine mortality rates in infants country 1 |  | 12 | [5 empty] | 0 | 0 | 0
Study 2: to determine prevalence and incidence of disease 1 in infants and children in country 1 |  | 12 | [5 empty] | 0 | 0 | 0
Study 3: Surveillance of resistance to antiretrovirals and management in country 3 |  | 12 | [5 empty] | 0 | 0 | 0
Study 4: Establishment of new cohorts of patients including high risk women |  | 12 | [5 empty] | 0 | 0 | 0
TOTAL COST BASELINE STUDIES (XAF) | [6 empty] | 15414989.5 | 0 | 9511376.5 | 0
TOTAL COST BASELINE STUDIES (EURO) | [6 empty] | 23500 | 0 | 14500 | 0
Support project activities |  | 24 |  |  |  |  | 3935742 | 4305342 | 7871484 | 0
Management of projet activities(Finance officer/PC/PM) |  | 24 |  |  |  |  | 15742968 | 70000 | 4460507.6 | 0
TOTAL COST NETWORKING ACTIVITIES (XAF) | [6 empty] | 19678710 | 4375342 | 12331991.6 | 0
TOTAL COST NETWORKING ACTIVITES (EURO) | [6 empty] | 30000 | 6670.1659 | 18800 | 0
Purchase of printers (3) |  | 24 | [5 empty] | 0 |  | 0
| purchase of IT material/ink for PM printer | 24 | [5 empty] | 60000 |  | 0
Purchase of Laptops (5) |  | 24 | [5 empty] | 600000 |  | 0
Purchase of desktops (2) |  | 24 | [5 empty] | 0 |  | 0
PURCHASE OF IT MATERIAL (XAF) | [6 empty] | 9470707.166 | 660000 | 4263720.5 | 0
PURCHASE OF IT MATERIAL (EURO) | [6 empty] | 14438 | 1006.1635 | 6500 | 0
[6 empty] | TOTAL ELIGIBLE COSTS (EURO) | 340692.7396 | 65317.4553 | 267860 | 71840
[6 empty] | OVERHEADS (administration: 10%) | 34069.274 | 19381.9259 | 26786 | 7184
[6 empty] | TOTAL ELIGIBLE COSTS INCLUDING OVERHEADS (EURO) | 374762.0136 | 84699.3812 | 294646 | 79024
[6 empty] | remaining funds (EURO) | 290062.6323 | 77.4%
NB: your Total eligible cost must correspond with the budget sent to you by your Funder

## Project REAL EXP. 1st semester
[5 empty] | RATE XAF/EURO | 655.957
FUNCTION | NAMES | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | TOTAL
Junior Medical Doctor TB | AFC |  |  |  |  | 300000 | [7 empty] | 300000
1 Post Doc disease 1 | [13 empty] | 0
1 nurse Lab disease 1 | BGT | [12 empty] | 0
2 interviewers for baseline studies | to be recruited | [12 empty] | 0
driver for field work | EN | [12 empty] | 0
1 Post Doc disease 2 | KLD | [12 empty] | 0
1 Junior Doctor disease 2 | to be recruited | [12 empty] | 0
1 nurse Lab disease 2 | to be recruited | [12 empty] | 0
Data Manager-Coordination | to be recruited | [12 empty] | 0
Local Coordinator disease 1 | Dr. XXX |  |  | 390000 | 390000 | 390000 | 390000 | [6 empty] | 1560000
Clinical researcher | KIL | 0 | 650000 | 650000 | 650000 | 650000 | 650000 | [6 empty] | 3250000
1 technician Lab disease 1 | MNP | [12 empty] | 0
4 PhD students | GON/ HVP/VNT/ENP |  |  |  |  | 780000 | 780000 | [6 empty] | 1560000
Bioststistician | KLJ | [12 empty] | 0
finance officer | AM | 0 | 87500 | 87500 | 87500 | 87500 | 87500 | [6 empty] | 437500
Project Manager | FVN |  |  | 1040000 | 1040000 | 1040000 | 1040000 | [6 empty] | 4160000
1 lab technicien disease 2 | to be recruited | [12 empty] | 0
Local Coordinator disease 2 | AMD | 0 | 325000 | 325000 | 325000 | 325000 | 325000 | [6 empty] | 1625000
TOTAL PERSONEL COST XAF |  | 0 | 1062500 | 2492500 | 2492500 | 3572500 | 3272500 | 0 | 0 | 0 | 0 | 0 | 0 | 12892500
car purchase for baseline study | [13 empty] | 0
CAR PURCHASE for studies |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perdiem local trips | [13 empty] | 0
Perdiem Long distance trips | [13 empty] | 0
office supply | [13 empty] | 0
trainers fee | [13 empty] | 0
Other fees | [13 empty] | 0
SUB TOTAL SEMINAR 1 (Molecular Diagnostics of disease 1 ) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perdiem local trips | [13 empty] | 0
Perdiem Long distance trips | [13 empty] | 0
office supply | [13 empty] | 0
trainers fee | [13 empty] | 0
Other fees | [13 empty] | 0
SUB TOTAL SEMINAR 2 (Preparation of SOP for disease 1) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perdiem local trips | [13 empty] | 0
Perdiem Long distance trips | [13 empty] | 0
office supply | [13 empty] | 0
trainers fee | [13 empty] | 0
Other fees | [13 empty] | 0
SUB TOTAL SEMINAR 3 (In vitro culture of Myc.Bac) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perdiem local trips | [13 empty] | 0
Perdiem Long distance trips | [13 empty] | 0
office supply | [13 empty] | 0
trainers fee | [13 empty] | 0
Other fees | [13 empty] | 0
SUB TOTAL SEMINAR 4 (drug resistance genotyping) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL COST SHORT TERM TRAINING for TB |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
renovation WC + office |  | 436700 | 538050 | 807500 | 167000 | [8 empty] | 1949250
Internet ( installation+monthly due)+ sattelite dish |  |  | 653950 | 353000 | 2940000 | 500000 | [7 empty] | 4446950
purchase / installation generator group | [5 empty] | 834000 | [7 empty] | 834000
renovation Hospital Laboratory | [13 empty] | 0
renovation Lab P2 University | [13 empty] | 0
TOTAL COST RENOVATION |  | 436700 | 1192000 | 1160500 | 3107000 | 1334000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7230200
Feezers, fridges, power supply, hoods, microscopes, PCR machines, electrophoresis equipment, HPLC machine, haematological analyser FACS machine | [13 empty] | 0
TOTAL COST LAB EQUIPMENTS |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Laboratory material (disease 1) | [13 empty] | 0
office supply & materials | [13 empty] | 0
car fuel and maintenance | [13 empty] | 0
patients cost | [13 empty] | 0
phone/fax/internet/mails | [13 empty] | 0
other exxpenses | [13 empty] | 0
TOTAL COST BASELINE STUDIES |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Perdiem missions PC/ webmaster |  |  | 487500 |  | 1215000 | 597888 | [7 empty] | 2300388
local langage course for students | [5 empty] | 541667 | 541667 | [6 empty] | 1083334
transport expenses (long distance trip) | [5 empty] | 921620 | [7 empty] | 921620
phone/fax/internet/mails | [13 empty] | 0
IT Equipment and printers | [13 empty] | 0
office material & supply | [13 empty] | 0
SUB TOTAL PROJECT SUPPORT ACTIVITIES |  | 0 | 487500 | 0 | 1215000 | 2061175 | 541667 | 0 | 0 | 0 | 0 | 0 | 0 | 4305342
Perdiem long distance missions | [13 empty] | 0
phone/fax/internet/mails |  |  |  |  | 20000 | 30000 | [7 empty] | 50000
IT equipments and printers | [13 empty] | 0
Matériel et fournitures de bureau | [5 empty] | 20000 | [7 empty] | 20000
SUB TOTAL PROJECT MANAGEMENT ACTIVITIES |  | 0 | 0 | 0 | 20000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70000
TOTAL COST NETWORKING ACTIVITIES |  | 0 | 487500 | 0 | 1235000 | 2111175 | 541667 | 0 | 0 | 0 | 0 | 0 | 0 | 4375342
printers purchase (3) | [13 empty] | 0
purchase of IT material/ink for PM printer |  |  |  |  | 60000 | [8 empty] | 60000
Purchase of Laptops (4) | [5 empty] | 600000 | [7 empty] | 600000
Purchase of desktops (2) | [13 empty] | 0
TOTAL COST IT MATERIAL |  | 0 | 0 | 0 | 60000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660000
[13 empty] | TOTAL EXPENSES | 25158042

## analasis of project expenses
| BUDGET YEAR 1 | REAL EXP. after 6 months | funds remaining | % of funds left | EXPENSES STATUS
TOTAL PERSONNEL COST | 59403465.92 | 7107500 | 52295965.92 | 88.04% | below expectations
TOTAL COST SUB CONTRACT | 26103638 | 10758690 | 15344948 | 58.78% | below expectations
OVERHEADS for administration (XAF) | 12793300 | 12713710 | 79590 | 0.6221% | above expectations, reevaluation needed
CAR PURCHASE FOR STUDIES | 16398925 | 0 | 16398925 | 100% | below expectations
TOTAL COST SHORT TERM TRAINING for TB | 27812576.8 | 0 | 27812576.8 | 100% | below expectations
TOTAL COST RENOVATION | 39357420 | 7230200 | 32127220 | 81.63% | below expectations
TOTAL COST LAB EQUIPMENT | 9839355 | 0 | 9839355 | 100% | below expectations
TOTAL COST BASELINE STUDIES | 15414989.5 | 0 | 15414989.5 | 100% | below expectations
TOTAL COST NETWORKING ACTIVITIES | 19678710 | 4375342 | 15303368 | 77.77% | below expectations
TOTAL COST IT MATERIAL | 9470707.166 | 660000 | 8810707.166 | 93.03% | below expectations
TOTAL PROJECT EXPENSES (XAF) | 236273087.386 | 42845442 | 193427645.386 | 81.87% | below expectations
TOTAL PROJECT EXPENSES (EUR) | 360195.9997 | 65317.4553 | 294878.5445
This template document has been freely provided by The Global Health Network. Please reference The Global Health Network when you use it, and share your own materials in exchange. www.theglobalhealthnetwork.org.

## real expenses sub contract
FUNCTION | NAMES | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC | TOTAL
accountant | AK | 75000 | 150000 | 150000 | 150000 | 150000 | 150000 | [6 empty] | 825000
secretary | SB | 100000 | 200000 | 200000 | 200000 | 200000 | 200000 | [6 empty] | 1100000
director | JVM | 0 | 180000 | 180000 | 180000 | 180000 | 180000 | [6 empty] | 900000
finance manager | AK | 0 | 162500 | 162500 | 162500 | 162500 | 162500 | [6 empty] | 812500
Purchase officer | ML | 0 | 0 | 175000 | 175000 | 0 | 175000 | [6 empty] | 525000
STAFF SALARIES |  | 175000 | 692500 | 867500 | 867500 | 692500 | 867500 | 0 | 0 | 0 | 0 | 0 | 0 | 4162500
other accomodation expenses | hotel | [5 empty] | 51665 | [6 empty] | 51665
ACCOMODATION EXPENSES |  | 0 | 0 | 0 | 0 | 0 | 51665 | 0 | 0 | 0 | 0 | 0 | 0 | 51665
scan, printing expenses |  | 9400 | 1800 | 14825 | 47800 | 21550 | 15000 | [6 empty] | 110375
telecommunication expenses |  |  | 6000 | 5000 | 67850 | 58900 | 15000 | [6 empty] | 152750
mailing expenses | [13 empty] | 0
fuel expenses | [13 empty] | 0
invitation expenses |  |  |  |  | 8400 | 247250 | [7 empty] | 255650
GENERAL FUNCTIONING EXPENSES |  | 9400 | 7800 | 19825 | 124050 | 327700 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 518775
furniture expenses | [13 empty] | 0
office material |  | 3000 |  | 87000 |  | 6000 | 15000 | [6 empty] | 111000
maintenance products |  |  | 44650 |  | 3000 | 1500 | 5000 | [6 empty] | 54150
office supply |  | 40500 | 49750 | 115850 | 69450 |  | 20750 | [6 empty] | 296300
OFFICE SUPPLIES |  | 43500 | 94400 | 202850 | 72450 | 7500 | 40750 | 0 | 0 | 0 | 0 | 0 | 0 | 461450
maintenance of transportation material | [13 empty] | 0
maintenance of IT material |  |  |  | 5000 | 50000 | 95000 | [7 empty] | 150000
maintenance of office material | [13 empty] | 0
maintenance of office furniture | [13 empty] | 0
MAINTENANCE /REPAIRS |  | 0 | 0 | 5000 | 50000 | 95000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150000
office furniture |  |  | 1032750 | 284400 | 99000 | [8 empty] | 1416150
IT material |  |  | 84000 | 1113900 | [9 empty] | 1197900
idustrial material | [13 empty] | 0
renovation work |  | 364500 | 1403150 | 5000 | 33000 | 2000 | [7 empty] | 1807650
transportation material | [13 empty] | 0
PURCHASE OF MATERIAL |  | 364500 | 2519900 | 1403300 | 132000 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4421700
staff trainings |  |  | 780000 | [10 empty] | 780000
STAFF TRAININGS |  | 0 | 780000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 780000
staff transportation espenses |  |  | 25000 | 30000 | 45400 | 23200 | 8000 | [6 empty] | 131600
TRANSPORTATION EXPENSES |  | 0 | 25000 | 30000 | 45400 | 23200 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 131600
custom expenses |  | 81000 | [11 empty] | 81000
TAXEX AND DUTTIES |  | 81000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81000
publication and media expenses |  | 260000 |  | 12500 |  |  | 150000 | [6 empty] | 422500
staff visit cards printings expenses |  |  |  |  | 110210 | [8 empty] | 110210
visa expenses |  |  |  |  | 35000 |  | 106000 | [6 empty] | 141000
diesel for generator | [5 empty] | 10000 | [7 empty] | 10000
fuel for project car | [5 empty] | 30000 | [7 empty] | 30000
purchase of project car |  |  |  | 12000000 | [9 empty] | 12000000
ADMINISTRATIVES COSTS/ OVERHEADS |  | 260000 | 0 | 12012500 | 145210 | 40000 | 256000 | 0 | 0 | 0 | 0 | 0 | 0 | 12713710
TOTAL EXPENSES SUB CONTRACT OFFICE |  | 933400 | 4119600 | 14540975 | 1436610 | 1187900 | 1253915 | 0 | 0 | 0 | 0 | 0 | 0 | 23472400

## analasis of sub contract budget
| BUDGET YEAR 1 | REAL EXP. after 6 months | funds remaining | % of funds left | REMARKS
STAFF SALARIES | 10973638 | 4162500 | 6811138 | 62.07% | on track
ACCOMODATION EXPENSES | 1625000 | 51665 | 1573335 | 96.82% | on track
GENERAL FUNCTIONING EXPENSES | 1865000 | 518775 | 1346225 | 72.18% | on track
OFFICE SUPPLIES | 4200000 | 461450 | 3738550 | 89.01% | on track
MAINTENANCE /REPAIRS | 2460000 | 150000 | 2310000 | 93.9% | on track
PURCHASE OF MATERIAL | 4280000 | 4421700 | -141700 | -3.311% | reevaluation needed
STAFF TRAININGS | 0 | 780000 | -780000 |  | reevaluation needed
TRANSPORTATION EXPENSES | 500000 | 131600 | 368400 | 73.68% | on track
TAXEX AND DUTTIES | 200000 | 81000 | 119000 | 59.5% | on track
SUB CONTRACT EXPENSES | 26103638 | 10758690 | 15344948 | 58.78% | on track
ADMINISTRATIVES COSTS/ OVERHEADS | 12793300 | 12713710 | 79590 | 0.6221% | reevaluation needed
TOTAL SUB CONTRACTED OFFICE (XAF) | 38896938 | 23472400 | 15424538 | 39.65% | reevaluation needed
TOTAL SUB CONTRACTED OFFICE (EUR) | 59297.9997 | 35783.4431 | 23514.5566